Ministry of Water and Energy, Water Resource Management Sector

Basin Scale Resilience Initiative for Ethiopia (BaSRINET) Project

Terms of Reference (ToR) for Consultancy service on

Identified Monitoring Site Assessment, Verification, Validation, Drilling Design and Drilling document preparation for Five Monitoring Wells Drilling work at Lower and Middle Awash, and Lower Wabi-Shebelle Sub Basins, Ethiopia

Prepared by

Ministry of Water and Energy, Groundwater Desk and BaSRINET Project Coordination Team

October 28, 2025

Addis Ababa, Ethiopia

Table of Content                                                                                                                                 Page No

1.	Introduction	1

1.1.	Background	1

1.2.	Rationale	2

1.3.	Objective	2

1.3.1.	General Objectives	2

1.3.2	Specific Objectives	2

2.	Scope of the Services	3

3.	Methodology	4

3.1	The Project site	4

3.2	Data sources and collection techniques	5

3.3	Tools and data analysis techniques	6

4	Detail activities description	7

5	Feature of the Work and Major Considerations and Requirement	15

5.1	Feature of the work	15

5.2	Major Considerations and Requirement	16

5.2.1	The Consulting firm	16

5.2.2	Professional Team Composition	16

5.2.3	Logistics requirement	20

5.2.4	Contract administration	20

6	Major Deliverables	22

7	Milestones, Schedules and Payment Modalities	22

8	ANNEXES	27

List of Figure

Figure-1 Project study site	5

List of Table

Table 1  Lists of Experts and Professional Requirement	17

Table 2 Shows Deliverable Report and Payment Modality	23

Table 3 Project Implementation Time Table Reporting Template	25

Table 4 Calculated maximum draw down of the well field for different scenario of exploitation rate and duration reporting template	27

Table 5 Numerical method scenario of exploitation reporting template	27

Table 6  Prediction numerical model outputs summary reporting template	28

Table 7 Drilling work specification and cost estimate reporting template	28

Table 8 Head work material specification and cost estimation (BoQ) reporting template	29

Table 9 Drilling input materials specification and cost estimation (BoQ) reporting template	29

Table 10 Basic monitoring wells characteristics	30

Table 11 Drilling methods and diameters of monitoring wells	30

Table 12 Summary of well depth vs specific capacity of the project	30

Table 13 Summary of monitoring wells data	31

Table 14 Summary of water chemical analysis results of the monitoring wells	31

Table 15 Lithological description of monitoring wells	32

Table 16 Electrical logging	33

Table 17 Casing arrangement	33

Table 18 Sieve analysis result by layers	34

Table 19 Preliminary pumping test data	34

Table 20  Step drawdown pumping test	35

Table 21 Summary of step drawdown test	35

Table 22 Constant rate test data	36

Table 23 Recovery pumping test data	37

Table 24 Chemical analysis result of monitoring wells	38

# Introduction

## Background

Groundwater is a strategic resource in all climatic regions of Ethiopia, contributing about 80% of the domestic supply of urban and rural populations and about 10% of the industry water supply source. The arid, semi-arid, and dry sub-humid areas of Ethiopia account for 70% of the total landmass and 46% of the total arable land. Drought and flood events, loss of grazing land, land degradation, changes in ecosystems and biodiversity, loss of livestock, water and food insecurity, and increased temperature and aridity threaten the hydrosphere's health and the general well-being of the population.

Salient groundwater information and monitoring at lowland arid areas are able to create drought resiliency, improve the welfare of the population, utilize the land resources, and provide sustainable agricultural production. In this regard, the use of groundwater for drinking water supply and/or irrigation practices is expected to result in far-reaching implications in ensuring resilient communities. The development of groundwater monitoring infrastructure has received considerable attention in relation to the objectives of MoWE's groundwater resources management. The advancement of groundwater resources management is highly dependent on the improvement of the groundwater information system. In Ethiopia, there were long-lasting hydrological stations on the surface water resources monitoring system, especially for the stream flow and dam/lake level gauge data collection and analysis of the quantitative potential of our surface water for different national socio-economic development purposes. However, there are a few infant-level groundwater resources monitoring systems.

Therefore, the desks decided to outsource the study and design of the five monitoring wells and supervision work of the monitoring wells during drilling by consultant.

## Rationale

The MoWE/WRM sector has studied and identified a long-term groundwater monitoring network and stations in its Basins Monitoring Strategic plan to sustainably monitor the real-time groundwater level, water quality trends, and aquifer characteristic changes and quantify the groundwater potential in space and time with regard to climate change, population growth, economic development, and other emerging issue scenarios. However, there is a limitation to the developed groundwater resources monitoring infrastructure due to the high management needs and the extensive areas of the country. Therefore, the BaSRINET project is planned to contribute to filling the gaps observed in groundwater resource monitoring under the comprehensive hydrologic basin water information system by drilling five monitoring wells at the lower and middle Awash, and lower Wabi-Shebelle project sites using service procurement.

## Objective

### General Objectives

The main objective of this study is to carry out an integrated hydrogeological and geophysical assessment for verification and validation of groundwater monitoring sites and drilling documents preparation at lower and middle Awash, and lower Wabi-Shebelle sub basins project sites.

### Specific Objectives

The specific objectives of the project work are summarized as follows:

- To determine the water balance of the area, hydrogeological condition of the site: evaluate recharge and discharge conditions, delineate spatial distribution of different aquifers, determines hydraulic parameters, analyze water quality of the aquifers and assess impacts of future exploitation of the potential aquifers.

- To assess the potential impacts of human activities and climate variability on ground water resources potential.

- To carry out analytical and/or numerical model of the main aquifer of the area and recommend appropriate groundwater exploitation and management.

- To develop the monitoring well design, work and construction material specification, BoQ and construction cost estimation, construction procedures and supervision strategy document preparation for both sites.

- To supervise drilling, casing arrangements, wells development, pumping test and equipping five wells at both lower Awash and Wabi-Shebelle sub basins and preparation well completion report for each well.

# Scope of the Services

The study focuses the monitoring site verification, validation, drilling design, drilling and supervision document preparation and supervision works during drilling of the monitoring wells at lower awash and Wabi-Shebelle sub basins.

The scope of this service is identifications of groundwater prospective sites, feasibility study and detail design preparation. All the activities shall be carried out as per the latest applicable & relevant codes and established practices such as international, regional and national groundwater investigation guidelines & manuals, sub national (regional states) standards & manuals and other standard manuals for the preparation of feasibility study and detail design of monitoring wells drilling and construction.

Moreover, the technologies to be proposed shall be appropriate to the project site hydrogeological contexts and the project objectives. All the study and design reports are expected to be of the required level of quality and shall be practical and appropriate to the site condition. The consultant shall submit all the raw and generated information annexes, detail design documents, drawings, general and technical specifications, Bills of Quantities, construction and workmanship cost estimates.

The work shall be carried out in five stages:

The First Stage (Stage I: Desk work) of the work is the Inception Stage, composed a review of previous works, overlay analysis to determine groundwater prospective areas, develop a conceptual hydrogeological model, a preliminary field visit, and submission of the Inception report.

The Second Stage (Stage II: Field verification and validation work) comprises all the existing field data of socio-economic and hydro geophysical surveys, geological and hydrogeological data collected in specified target areas to verify the selected sites for monitoring wells drilling, design, and cost estimation.

During the Third Stage (Stage III: post field work), a detailed hydrogeological analysis shall be conducted at a specific target area that shall be drilled to monitor the groundwater resource; evaluation and management activities that include determination of aquifer parameters and estimation of total exploitable groundwater resource together with analytical and/or numerical groundwater modeling used for groundwater management shall be carried out and preparation of the drilling design and construction specification and BoQ preparation and procedures for drilling materials provisions and supervision work are evaluated & finalized.

Stage IV: Drilling  and Supervision work: all pre requisites, including  the machinery, specified construction materials, and inputs resources, are procured and organized for mobilization to the sites drilling, and drilling supervision work takes places simultaneously. Development of template forms for the drilling supervision, and site handing over to drilling company.

In Stage V: well completion reports and handing over the water well development, pump test, finishing, and resources demobilization to the offices.

# Methodology

## The Project site

The proposed assessment sites are situated in Lower and Middle Awash and Lower Wabi-Shebele sub-basins. The project study site is shared by three regional states, Afar, Somali, and Oromia, and site is characterized by low lying arid to semi-arid ecological character.

Figure-1 Project study site

## Data sources and collection techniques

In this study the secondary data of various sources and the primary data are required. The water level, pH, EC, temperature, geophysical data and other existing situation of the study area are the primary data to be collected in field observation and direct measure, key informant interview, focal group discussion and reconnaissance survey techniques will be expected. The meteorological data (precipitation, temperature and other weather data), hydrological data (stream flow, infiltration and evapotranspiration losses), population and water use data, existing water wells and wells completion reports, spatial data (soil, LULC, geomorphology, DEM, Imageries, shape files), hydrogeological data (hydraulic conductivity and transmissivity) are the secondary data to be collected from EMI, MoWE, CSA, GSSI, GWD and WFC respectively using office visit and electronic devices.

## Tools and data analysis techniques

The study need to deploy integrated techniques and approaches to analyze and interpret the meteorological data, soil and LULC data, terrain and geomorphological data, hydrological data, geology and hydrogeology data, geophysical data, socio economic data to confirm the identified appropriateness and in place the water well drilling site for monitoring purpose at specified site in the selected area. The preliminary desk review of previous work, data consistency, homogeneity and accuracy in quality analysis, integrated conceptual modeling, base flow separation, recharge estimation, water balance, overlay analysis mapping techniques will be clearly expected in data analysis and tables, diagram, plots and maps will be expected to present the result interpretation.

Spread sheet, DEM, Arc/QGIS, SWAT, Global Mappers, Surfers, Google engines, Satellite imagery, Wets pass, MODFLOW, 3D groundwater modeling tool, VES, EM, TEM, ERT,  AutoCAD and statistical tools are expected for hydro-met data analysis, water balance analysis, multi criteria analysis, trend analysis, recharge estimation, groundwater flow conceptualization, geophysical data analysis, well drilling design and socio-economic analysis.

The DTH and air/ mud rotary drilling techniques or other techniques will be deployed accordingly. The monitoring wells drilling, pumping test and well development process requires viscous meter/mud funnel, PH meter, EC meter, booster and compressor.

The project work has two major components, and it is a mixture of LUMP SUM and TIME-BASED CONTRACT:

- Groundwater Monitoring sites verification and design and

- Detail drilling site study, drilling design, material provision and drilling work for all monitoring sites at both sites  (3 and 2 monitoring Wells at Awash and Wabi-Shebelle respectively)

# Detail activities description

The proposed methodology for the groundwater resources monitoring sites verification is require an integrated approach and multidisciplinary team set up for data collection, review, field survey, identification, selection and evaluation of the identified monitoring stations at both project sites. The proposed study should focus on evaluation of the prospective groundwater monitoring sites on the ground through detailed, comprehensive and integrated methods and will be completed in five stages:

Phase-I Groundwater Resources Prospective Site Prioritization, Evaluation and Drilling Design and Quantification (4 months)

- Stage I: Desk work & Inception Report.(1month)

- Stage II: Field Work: detail Assessment and site verifications. (2  months)

- Stage III: Post Field: build up on the framed deskwork and detail analysis, preparation of drilling design specification, BoQ (Bill of Quantity) and Bid document for the drilling of the five monitoring wells.(1 months)

Phase -II Drilling and Supervision (9 months)

- Stage-IV: Construction Materials Mobilization / input provision, Drilling (Well development, Pump test, Finishing work and supervision of drilling work) (8 months)

- Stage-V: Well completion report preparation, handing over and Materials demobilization (Soft Side work) (1 month)

- Phase-I Groundwater Resources Prospective Site Prioritization, Evaluation and Drilling Design and Quantification

Stage I: Pre field/ Desk work and inception report phase

- Preliminary gathering and review of previous works of the area including study documents by academic researcher, research institutes, geological and hydrogeological maps (1:250,000 to 1,50,000 scales by EGS and MoWE), Hydrogeological and groundwater potential study at national, regional and continental level, at basins and sub basin level and all other relevant documents

- Collection. sorting and organizing secondary data of  different sources such as agro ecology and climate data (rainfall, Daily maximum and minimum temperature, Relative humidity, wind speed, Sunshine duration and etc.), hydrological data (stream flow and soil moisture), Groundwater data  (complete borehole data including drilling log and pump test data),   socio-economic data (human and livestock population data, settlement pattern, water use data). Environmental and geospatial data (LULC, Soil and topography), organizing various data analysis tools and software

- Develop the skeleton of study document and structuring the contents to addressed in study procedures, as well as preliminary analysis of various secondary data in to plots, maps and figures presentation and preparation for primary field data collection proposal and field survey techniques

Develop various maps (location, soil, land use land cover, hydrology (stream pattern, density), topographic and geomorphology, geology, hydrogeology, settlement and water well distribution maps),  surveying route and data collection check lists, organizing tool kits, scientific hand tools, notebooks and logistics arrangement.

- The general steps involve high resolution maps: so, 1:50,000 mapping scale for the entire the catchment will be produced and 1:10,000 mapping scales for catchment to be delineated for drilling operation

Stage II: Field Work (detail Assessment and site verifications)-2  month

- Trip to field and deal with local technical experts at woreda offices for accessibility information, awareness creation on the field work objectives, field data collection procedure and the goal of the study.

- Socio-economic data collection through field observation, key informant interview and focal group discussion, historical and expertize technical judgement as well as prioritizing the community problems, gaps and needs toward groundwater resources management and uses.

- Transect walk to assess and verify the identified monitoring well sites and surveying transverse line selection and geophysical data collection using VES, TEM and ERT geophysical equipment.

- Observation of soil and geomorphological features set up and types  (granules, fractures, faults, cavities, lining aspects and complexity of the formation) in relation to groundwater flow indicators and verify the geological classes identified on the generated maps  and collection rock samples for crystal analysis at lab for the detail catchment study

- Observation of hydrological pattern, degradation status, pollutant sources and the presences important ecosystem (wetland, springs, vegetation covers) verification of analyzed secondary data of the generated maps on the desk work

- Observation of the existing groundwater development, uses and collection of field measurements such as actual water level, EC, PH, Temperature, and verification for the existing water wells and springs distribution Identified on the generated map on the desk work

- Perform all necessary actions, contact and approaches to exhaustively address the field data collection objectives to produce comprehensive and sound groundwater availability and design information to enhance the effective resources mobilization, drilling works and supervision phase

- Progress reports on the technical achievement at the field, challenges and measures taken during this milestones

Stage III: Post field (build up on the framed deskwork and detail analysis, drilling design specification and BoQ preparation) (1 months)

- Sorting, organizing and linking the collected primary data with the analyzed secondary data during desk work

- Water balance analysis (inflow, outflow, change in GW storage), infiltration / recharge estimation, current discharges estimation at existing water wells and permissible yield analysis in the catchment area of the project

- Detailed analysis of meteorological data, Hydrological data, land use land cover data, soil data, geological data, geophysical data, hydrogeological data, socio-economic data and all technical consideration using multi criteria overlay analysis techniques and approaches through

- Preparation of physical thematic layers required for multi criteria overlay analysis of study area and determining the significant layers

- Reclassifying or transforming the data within a layer  and weighting the input layers parameters

- Combining the layers and analyzing the weighted results

- Delineation and mapping of the catchment  and validation by collected ground truth data

- Model conceptualization, monitoring site evaluation, and drilling techniques selection

- Map and verify hydrogeological boundaries and units (hydrogeological mapping at 1:10,000 based on the extent of potential areas)

- Interpretation and calibration of the geophysical survey results using drilling log results of the monitoring wells

- Aquifer characterization and determination of aquifer parameters and evaluation of the water quantity and quality of the monitoring wells

- Summarizing all drilling techniques and analysis results and developing water well drilling design, quantity survey and water well construction specification and BoQ preparation.

- Preparation of  water well drilling design and resources mobilization schedules.

Phase II Drilling and Supervision (9 months)

Stage IV: Construction Materials Mobilization/ input provision, Drilling (Well development, Pump test, Finishing work and supervision of drilling work) (8 months)

During this stage, the contractor must mobilize all construction workmanship (drilling crew), construction materials and scientific equipment’s, different sizes of drilling rods and beats, casings (surface and inner casing, fittings, collars and subs, drilling fluids, and other well development accessories and safety tools) to both Awash & Wabi-Shebelle project sites based on the design developed and surveyed quantity in stage III.

The consultant must evaluate the drilled monitoring wells through well development and pumping test in line with the theoretical result inferred under Stage III.  The contractor drill the monitoring wells and pass through pump test of the aquifer evaluation procedures and all the water well development stages at the identified sites on the groundwater monitoring strategic document and deploy detail modeling analysis, water quantity and quality evaluation and various scenarios development.

The MoWE Groundwater Management Desks and the BaSRINET Project Responsible Expert will follow-up and evaluate the overall study and drilling activities at Lower Awash and Wabi- Shebelle sub basins based on the study ToR and Drilling Design specification, Time table and Evaluation criterion developed to assure the standards and expected work quality. Specifically for the consultancy services while the consultant should technically supervise the drilling work based on the study documents and standard operational manual developed during the groundwater potential study phase to gather critical data and bear in time decision measures. Therefore, the consultant shall:

- Supervise the drilling and testing activity of all monitoring wells at both Lower Awash and Wabi- Shebelle sub basins as per the construction procedures and technical details intended  to assure the standard and work quality hence avoid extravagancy may happen in terms of cost, time and scope management.

- Supervise the fulfillment of all human and material resources required for the drilling work and safety measures to perform in the planned cost and time as per the agreement document and construction contract management rules

- The supervision is mainly critical on the technical issues including cross checking of drill design and drilling techniques proposed, sample measurements (temperature, PH, Viscosity and fluid density), lithological log management (sample takin depth interval, log arrangement and handling), application of pumping test procedures and timing, gravel arrangements and well development safety, inner casing arrangement in line with lithological & electrical logs, appropriate water quality sampling &reporting, and headwork construction processes.

- Ensure the achievement of the milestones and prepare payment certificates as per the milestone developed on the payment schedules and promote the work accordingly.

- Five Monitoring Wells Drilling

Groundwater resource evaluation monitoring well drilling at the verified sites shall be carried out simultaneously based on the objectives, well drilling design and procedural specification documents and all of them will have 500m depth both at Lower and Middle Awash, and Lower Wabi-Shebelle sub basins project sites. In the project documents three monitoring wells at Lower & Middle Awash sub-bsins, and the rest will be at Lower Wabi-Shebelle sub-basin at the prioritized prospective groundwater potential sites and used for groundwater resource evaluation. Such wells are also very important to generate site specific data and help as monitoring wells, domestic/ irrigation water supply for the community use.

The Consultant should ensure whether the contractor fulfills the following tasks during the drilling and pumping test activity;

      - Mobilize all resources and critical logistics required for the project implementation (human, materials and financial) resources for both project sites simultaneously.

      - Measure and collect important data (mud density and viscosity of the drilling fluids, lithological log, geophysical logs, electromagnetic logs, gamma analysis) during drilling of the monitoring wells at both project sites.

      - Accordingly organize all the casing arrangements and install observation pipes for all wells.

      - Collect and lab. analyzes all water quality parameters including temperature, PH, EC, TDS, Total hardness and others as per the WHO and Ethiopia water quality standard

      - Perform all step drawdown, constant rate and aquifer recovery pump test and record all carefully

      - Prepare borehole completion report, including annexes, vertical section drawings of completed borehole together with geologic log, pumping test data and their analysis, water quality and their analysis, groundwater evaluation summary tables various stages, raw excel data etc. and then submit to the Client.

    - Monitoring Wells Evaluation

The monitoring wells evaluation includes using the meteorological data analysis, hydrological and water balance analysis, soil and land use land cover analysis, socio-economic activities and environmental analysis. In this stage the evaluation mainly based on the outcome from the drilling well development and pumping test results, flow conceptualization model and calibration by ground truth (water levels, discharge, lithological logs, hydraulic conductivity, transmissivity, electrical conductivity, magneto telluric data, electrical logs) and  evaluation of the quantity and quality of groundwater of the monitoring sites through the interpretation and calibration of model results, and different scenarios development. Then characterize the intra and inter annual groundwater recharge dynamics under the current and predicted effects of climate change. Estimation of the total exploitable groundwater resources in the catchment area, and discuss the temporal changes in groundwater levels under current and future climate change and development scenarios (under the current and predicted effects of climate change). Present and discuss findings to stakeholders of the Stage-IV at a validation workshop. Prepare and submit the final Stage-IV report based on the outcome of the Workshop.

Stage V: Well completion report preparation, handing over and Materials demobilization (Soft Side work)-1 month

- Infrastructure development, knowledge and skill transfer

The consultant shall design salient strategies to sustain the project results and build the capacity of the client (MoWE) and regional bureaus technical staff to independently investigate and /or explore the groundwater resources management and development issues. The consultant shall organizes stage based training and joint field implementation plan that support the client (MoWE staff) to evaluate technical work, design and quantify the drilling requirements, develop phased monitoring indicators and supervision frame for similar projects. Therefore, the consultant must organize technical training for MoWE and respective regions accordingly on:

- Provision of groundwater data loggers, sample collection tool kits (borehole camera, deep meter, VES, viscous meter, PH meter, metal / flame meter) and installation

- Training on groundwater resources data collection instrument selection and sampling technical skill

- Training on techniques of telemetric data loggers installation and calibration skill

- Training on time series data analysis  and 3D groundwater conceptual modeling skill

- Data and Information Management

The Consultant’s team shall prepare and organize all the datasets collected and generated during the project life, and will develop database for two project sites, Lower & Middle Awash, Lower Wabi-Shebele sub-basins, and link with the central database. The details are listed as follows:

Therefore, the BaSRINET monitoring wells drilling project shall prepare and organize all the datasets collected and generated during the project life in the database as knowledge hub.

- The Meta data, raw data, field measurements, datasets and the generated information shall be collected in developed and agreed templates of format to organize in the database for future consumption.

- The equipped monitoring wells and the selected monitoring instrument shall be organized and presented in scientifically standardized publication reports and serves as a reference points for further researches in the area.

- Organize the project good practices obtained and challenges faced during the implementation phase and clearly indicate the approaches and techniques deployed in groundwater monitoring drilling

- Ensure project  added value and outcome add on information in the groundwater resources database, modeling practices and information management system

- Organize the project key findings, improved information and changes achieved in building climate changes resilient groundwater resources management system  including (estimated recharge, hydrogeological maps, hydro-geophysical maps, hydro-geochemical maps, well completion reports), analytical table, figures and graphic summary presentation

# Feature of the Work and Major Considerations and Requirement

## Feature of the work

The groundwater resources management is among complex and full of uncertainty to achieve the intended objectives due to complex geological formation of unseen structural behaviors and groundwater flow system dynamics.  The well-designed groundwater monitoring system requires technical skill & experience, full supply of study scientific equipment (ATM and TEM of lithological layer detection and Electro-magnetic field analysis) and scientific tool kits (GPS, deep meter, aquifer layer detector) for field data collection and high capacity laptop and desk top computers, storage devices and essential software for data analysis while high performance and deep drilling capacity rig machines, different type and size drilling equipment, well equipped and organized supply management team, dedicated project coordination unit and readymade decision maker  to achieve the project goals.

## Major Considerations and Requirement

### The Consulting firm

For the BaSIRNET project groundwater component proposed at lower Awash and Wabi- Shebelle project sites MoWE Groundwater Exploration & Modeling and Groundwater Study & Design Desks are jointly decided to out sources the verification, validation and drilling of five monitoring wells at appropriate sites specified on the basin monitoring strategic document for the technical best fit contractor/company under the following major consideration and presence of

- Strong integration and high level of commitment and responsibility for scientifically sound & quality deliverables

- Dedicated project coordination unit and capable to final deliver within the given time scale.

- Firms with dedicated field working facilities, scientific equipment and field tool kits for comprehensive exploration works

- Strong professional firm and on jobs knowledge and skill transfer experience to client team

- Multidisciplinary team composition and experiences in working at groundwater exploration study and design work where multilayer alluvial deposited and harsh area

- Experiences in quality work delivery in short time without hesitation under tighten condition with full water well drilling design, work specification and bill of quantity

- Stand by to accept technical comments and take timely amendment and delivery.

### Professional Team Composition

The works is planned to implement at Lower and Middle Awash, and Lower Wabi-Shebelle river sub basins. Most probably there will be a five groundwater monitoring well drilling sites three at Awash and two at Wabi-Shebelle project sites respectively. Therefore, the selected firm will expected to have verification team and the following team composition with the specified requirements.

Table 1 Lists of Experts and Professional Requirement

| No | Job Title | # | Qualification & Education | Specific Experiences | General Experience | Time- Month |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Manager/ Team Leader | 1 | MSc in Hydrogeology/ Hydraulic /Water Resources Engineering | At least 10 years of specific experiences in hydrogeology and groundwater development management of which 3 years in management of drilling operation and contract administration works | At least 12 years of general experience in Infrastructure Construction, Study and Design of Water Supply in WaSH/WRM/ Irrigation or construction sectors | 13 |
| 2 | Senior Hydrogeologist/ Senior Groundwater Modeler | 1 | MSc in Hydrogeology | At least 8 years of specific experiences in hydrogeological investigation, groundwater mapping and development, groundwater modelling, interpretation of geophysical results, borehole design and groundwater development, drilling supervision, contract administration able to work with water resource software (ArcMAP, QGIS, Aquifer Test, Aquachem) | At least 10 years of general experience in groundwater source investigation, Study and Design of Water Supply in WaSH/WRM/ Irrigation or drilling sectors | 13 |
| 3 | Senior Geophysicist | 2 | MSc in Geophysics or related fields | At least 8 years experiences in geophysical application to water source mapping (groundwater investigation and borehole logging), analysis and interpretation, able to apply various geophysical exploration methods, experience in borehole geophysical logging | At least 10 years general experiences in geophysical investigation for groundwater exploration in WaSH/WRM/ Irrigation or construction sub sectors | 13 |
| 4 | Senior Hydrologist | 1 | MSc in Hydrology/ Water Resources | At least 8 years of specific experience in hydrological studies and projects including fieldwork, data analysis and modelling, able to use various hydrological software (HEC-RAS, HEC- HMS, SWAT) to model surface water interaction | At least 10 years of general experience in streamflow and river studies, watershed management, flood risk assessment, climate impact studies, adaptation strategies, integrated water resources management (IWRM) | 4 |
|  |  |  |  | with groundwater, skill in GIS and Remote sensing |  |  |
| 5 | Senior RS & GIS Expert | 1 | MSc in RS & GIS or related fields | At least 8 years of in GIS and Remote Sensing, experience in various GIS and Image analysis software, use and analysis of various satellite images | At least 10 years of general experience of GIS, Remote Sensing or relevant mapping experience in water supply works and resource mapping, WaSH/WRM/ Irrigation or construction sectors | 4 |
| 6 | Senior Socio- economist | 2 | MSc Degree in Sociology or relevant and related fields | At least 8-years of specific experiences in socio- economic study works in the water sector | At least 10-years of general experiences in socio- economic study and design of Water supply projects of WaSH/WRM/ Irrigation or construction sectors | 4 |
| 7 | Senior Environmentalist | 1 | MSc in Environmental Engineering or related fields | At least 8-years of specific experiences in Environmental study works in the water sector | At least 10-years of general experience in Environmental study | 4 |

Table 2 Proposed positions of the Consultants staff with maximum man-month for the service

| SN | Proposed Position | Person | Person-Month (PM) |  | Total Person- month | verification phase | Drilling phase | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Office | Field |  |  |  |  |
| 1 | Principal investigator / Team Leader | 1 | 3 | 1 | 4 | 4 |  | The site study and verification will be done parallel at both Awash & Wabi-Shebelle sites for 4 months respectively |
| 2 | Senior Hydrogeologist/ Senior Groundwater Modeler | 2 | 3 | 1 | 4 | 4 |  |  |
| 3 | Senior Geophysicist | 2 | 3 | 1 | 4 | 4 |  |  |
| 4 | Senior Hydrologist | 2 | 3 | 1 | 4 | 4 |  |  |
| 5 | Senior RS & GIS Expert | 1 | 3 | 1 | 4 | 4 |  |  |
| 6 | Senior Socio-Economist | 2 | 3 | 1 | 4 | 4 |  |  |
| 7 | Senior Environmentalist | 2 | 3 | 1 | 4 | 4 |  |  |

### Logistics requirement

The groundwater investigation works are full of unforeseen and uncertainties to exactly place the well drilling sites at the required accuracy to extract the intended water amount from the aquifer. Therefore, to approximate to the point the works require extensive site assessment and thorough investigation of physical observation, reconnaissance survey, field measurement collection, sample collection, and interviewing key informant groups for socio-economic data collection and so on.  Therefore, the consulting firm should have minimum

- Own dedicated field vehicles to commence the work immediately

- Audio Magneto Telluric (AMT) and Magneto Telluric (MT) geophysical equipment to collect geophysical and lithological strata information at deep alluvial formation,

- Other scientific field data collection tool kits (GPS, Deep meters, VES,  PH meter, EC Meter, geological hammer, water quality sampling tool kits, etc)

### Contract administration

The contract administration and the awarding of contracts is regulated and governed in accordance with the laws of the Public Procurement Proclamation (No. 649/2009) for public bodies and the Civil Code for administrative contracts like public works, supplies, and concessions. The process includes a clear timeline, defining procurement needs to final contract award and performance, and requires consideration of factors like bid price, project experience, and staff qualifications

- Bid Document Evaluation and Selection Criterion

The MoWE, Groundwater Resources Management Desks, and BaSRINET Project Joint Technical Team fully adapt the combined criteria of the Ethiopian Public Procurement and Property Administration Agency (PPA) and the Ethiopian Ministry of Science, Technology, and Innovation to evaluate consultancy service procurement.

The Ethiopian Public Procurement and Property Administration Agency (PPA) uses certain evaluation criteria for consultancy services, usually following a two-step process (technical and financial) as part of methods like Quality and Cost-Based Selection (QCBS).

- The key Eligibility evaluation criteria for technical proposals generally include:

        - Firm's Experience/Qualifications: The general experience of the consulting firm in the relevant field and under similar conditions, preferably within Ethiopia.

        - Adequacy of the Proposed Methodology and Work Plan: The quality, clarity, and suitability of the consultant's proposed approach, work plan, and implementation schedule to achieve the project objectives.

        - Qualifications and Competence of Key Staff: The educational qualifications, professional certifications, and specific experience of the personnel assigned to the project. The majority of proposed professional staff is expected to be permanent employees or have a stable working relationship with the consultant.

        - Transfer of Knowledge (if applicable): Any proposed plan for the transfer of knowledge or capacity building may also be a criterion depending on the nature of the assignment.

Evaluation Process:

  - Eligibility Check: Bidders must first meet basic eligibility requirements, including a valid business license, VAT registration certificate (for domestic firms), and a valid tax clearance certificate.

  - Technical Evaluation: Technical proposals are evaluated based on the criteria mentioned above and assigned a score. A minimum qualifying technical score is usually required to proceed.

  - Financial Proposal Opening: Only the financial proposals of firms that meet the minimum technical score are opened.

  - Financial Evaluation: Financial proposals are evaluated for cost-effectiveness and compared.

  - Combined Evaluation (QCBS): For QCBS, the technical and financial scores are combined using predefined weights to determine the final ranking. The highest-scoring firm is selected for contract negotiations.

  - Ethical Standards: Throughout the process, consultants are required to adhere to high ethical standards, and any engagement in corrupt or fraudulent practices leads to disqualification and potential debarment.

# Major Deliverables

The study team will deliver the following

- Full assessment and verified groundwater monitoring sites reports of both Awash & Wabi Shebelle project sites

- Full water well drilling design and material specification documents of both project sites

- Construction materials Bill of Quantity and schemes unit cost estimation documents

- BoQ of drilling inputs and head work construction materials document,

- Summary of project cost estimation, construction procedures and operational document for the project implementation

- Catchment water balance summary, quantitative and qualitative groundwater availability summary, Hydrogeological shape files, Geological shape files, Hydro chemical shape files  and all maps

- Data loggers specification,  installation guide and user’s manual

- All collected  raw and metadata files

- Annex data of study documents in spread sheets for both sites

- Five drilled monitoring wells completion report

- Five telemetric data loggers equipped and functional monitoring wells of 500m depth.

# Milestones, Schedules and Payment Modalities

The required contracting service is expected to last for a maximum of 13-months. Of this, 4-months are allocated groundwater prospective site evaluation and 9-months for drilling of monitoring wells and MoWE is responsible for supervision of the study and drilling of monitoring wells. The drilling and pumping test result will be used to realize the achievement of overall groundwater monitoring wells drilling it has to be completed within the allocated time. It is, however, the responsibility of the Contractor to establish a detailed work program within the above time frame, taking into consideration the estimated man-month requirements. This should be guided by their professional judgment of the assignment’s requirements and knowledge of the local conditions and needs.

Table 2 Shows Deliverable Report and Payment Modality

| SN | Deliverable (Report) | Deliverable Contents to be included but not limited to | No. of Hard Copies (soft copy) | Time frame from commencement date (C) (Month) | Payment Schedule |
| --- | --- | --- | --- | --- | --- |
| PHASE I – Study and Design (4-moths) |  |  |  |  |  |
| 1 | Draft Inception report (Stage-I) | The report includes: Intensive review of available documents and collected secondary data, different thematic layers for multi-criteria overlay analysis delineated groundwater potential zones preliminary conceptualize | 4 Hard Copy 1 Soft Copy | C+0.5 | 20% |
|  |  | hydrogeological models (Cross-sections and hydrogeological maps 1:100,000), identified data gaps for further phase works and proposed methodology and final work plan for the next Stages |  |  |  |
|  |  | Review the draft report and forward comments to the consultant (1 Week) |  | C+0.75 |  |
| 2 | Final Inception report (Stage-I) | Final inception report submission after incorporating comments/feedbacks of Workshop-1 | 4 Hard Copy 1 Soft Copy | C+1 |  |
| 3 | Detailed field survey report for selected prospective area (s) (Stage-II) | Comprises; inventory water points data, identified aquifers, source, rate and mechanism of recharge, discharge condition, geological and hydrogeological maps (1:10,000) with Cross-sections, geophysical, geo-electrical & pseudo- sections, regional as well as local groundwater flow systems, estimated hydraulic properties of identified aquifers, surface-groundwater interaction conditions, maps showing selected sites for monitoring wells drilling, drilling design. drilling techniques & work specification and bill of quantity borehole drilling documents | 4 Hard Copy 1 Soft Copy A0, A1 and A3 maps | C+2.5 | 20% |
|  |  | Review the draft report and forward comments to the consultant (2 Weeks) |  | C+2.75 |  |
| 4 | Final submission of report (Stage-II) | Final field verification report submission after incorporating comments/ feedbacks from the Workshop-2 | 4 Hard Copy 1 Soft Copy | C+3 |  |
| Phase II - Drilling of Monitoring Wells and Supervision phase ( 9 months) |  |  |  |  |  |
| 5.1 | Quality Standard manual | 1 Month from commencement of Stage 4 for the Draft and within two weeks of receipt of Client comments for the Final. | 4 Hard Copy 1 Soft Copy | Draft C+4 Final C+4.5 | 25% |
| 5.2 | Bi-Monthly Progress Report and Drilling Supervision Report | The 1st week of every two (2) months except the commencement, the Quarters and the End of Project | 4 Hard Copy 1 Soft Copy | C+5.5 |  |
| 5.3 | The monitoring Wells Drilling Completion Report | Two weeks prior to issuance of provisional Completion of Works | 4 Hard Copy 1 Soft Copy | C+7.5 |  |
| 5.4 | Project Completion and Final equipped monitoring wells hand over Report | Two weeks after commissioning of works | 4 Hard Copy 1 Soft Copy | C+8.5 | 35% |
| 6 | - Retention works | - The work of quality checks and assurance by guarantying of the construction and instrumentation |  |  | 5% |

All reports shall be submitted in both soft (MS Word, PDF) and hard copies. The hard copies will be prepared in A4 format, except for plans and drawings which should be prepared in A3 format. In addition, maps have to be prepared with A0, A1 and A3 size paper in five (5) copies. The reports should be clearly labelled, i.e., title of the study indicated, for easy identification and documentation purposes. All reports shall be prepared in the English language. Please note that the Consultant will be expected within one (1) week of submission of draft reports (Stage-I, II, III) to make presentations to the respected stakeholders. At each workshop, the Consultant shall make PowerPoint presentations, provide concise background documents for discussion and prepare workshop reports to document the proceedings. All cost of the venue and Client-side participants of workshop will be covered by the Client and place of the workshop shall be as appropriate. Numbers of participants may be till 30 but all fees of the participants from the Consultant side (transportation and per diem) will be covered by the Consultants.

Table 3 Project Implementation Time Table Reporting Template

| Ministry of Water and Energy National Integrated Water Resources Management Program BaSIRNET Project Implementation schedules |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BaSIRNET Project Groundwater Components Implementation Time frame |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| S/No | Major Activities description | Implementation Period |  |  |  |  |  |  |  |  |  |  |  |  |  | Remark |  |
|  |  | 2025 |  | 2026 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |
| 1 | Groundwater investigation, well siting and drilling design work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Equipment and construction materials mobilization to site |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Water well drilling and Construction work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Finishing work and resources demobilization to office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# ANNEXES

Table 4 Calculated maximum draw down of the well field for different scenario of exploitation rate and duration reporting template

| Scenario | Well discharge |  | Number of Wells in the well field | Total discharge of Well field |  | Calculated maximum drawdown at the center of the well field for different period of exploitation |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | l/s | m3/day |  | l/s | m3/day | 2000 days | 5000 days | 8000 days | 10000 days |
|  |  |  |  |  |  | 5.5 | 13.7 | 21.9 | 27.4 |
| 1 |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |

Table 5 Numerical method scenario of exploitation reporting template

| Scenario | Number of wells in each scenario | Proposed discharge of each well, l/s | Total Abstraction |  |
| --- | --- | --- | --- | --- |
|  |  |  | l/s | m3/s |
| I |  |  |  |  |
| II |  |  |  |  |
| III |  |  |  |  |

Table 6  Prediction numerical model outputs summary reporting template

| Scenario | Well discharge |  | Number of Wells in the well field | Total discharge of Well field |  | Calculated drawdown at the center of the prioritized site |  |  |  | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | l/s | m3/day |  | l/s | m3/day | 365 days | 1825 days | 3650 days | 5475 days |  |
|  |  |  |  |  |  | 1 years | 5 y | 10 y | 15y |  |
| 1 |  |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |  |

Table 7 Drilling work specification and cost estimate reporting template

| S/No | Activities description | Unit of measurement | Quantity | Unit rate | Total price | Remark |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |

Table 8 Head work material specification and cost estimation (BoQ) reporting template

| S/No | Item description | Unit of measurement | Quantity | Unit rate | Total price | Remark |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |

Table 9 Drilling input materials specification and cost estimation (BoQ) reporting template

| S/No | Item description | Unit of measurement | Quantity | Unit rate | Total price | Remark |
| --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |

Table 10 Basic monitoring wells characteristics

| Well Index |  |
| --- | --- |
| Well depth, m |  |
| Static water level ,m |  |
| Pumping test Pump position, m |  |
| Pumping test discharge ,l/s |  |
| Pumping test Pump power, Kw |  |
| Maximum drawdown, m |  |
| Dynamic Water level ,m |  |
| Transmissivity ,m2/day |  |
| Conductivity ,m/day |  |
| Specific capacity, l/s/m |  |
| Safe Yield , l/s |  |
| Well Type |  |
| Main Aquifer |  |

Table 11 Drilling methods and diameters of monitoring wells

| Depth interval | Drilling diameter | Drilling system | Casing used |
| --- | --- | --- | --- |

Table 12 Summary of well depth vs specific capacity of the project

| Site Name | Depth, m | Discharge, l/s | Draw down, m | Transimisivitym2/d | Specific capacity, l/s/m |
| --- | --- | --- | --- | --- | --- |

Table 13 Summary of monitoring wells data

| Water Point Index | Location | UTM-E | UTM-N | Elevation | Depth, m | SWL, m | Discharge, l/s | Draw Down, m | Specific Capacity, l/s/m | Transmissivity,m2/day | Conductivity, m/d | Driller | Drilling started | Drilling completed | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table 14 Summary of water chemical analysis results of the monitoring wells

| ID | Depth(m) | TDS | EC | ph | NH3 | Na | K | Ca | Mg | Fe | Mn | F | CI | No3 | Co3 | HCo3 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table 15 Lithological description of monitoring wells

| No. | Lithological Description | Depth interval (m) |  |
| --- | --- | --- | --- |
|  |  | From | To |

Table 16 Electrical logging

| WELL ID: |  | Well name |  |  | REFERENCE |  | 1m |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CHIFE DRILLER: |  |  |  |  |  |  |  |  |
| DEPTH: |  |  |  |  |  |  |  |  |
| LOGGING METHOD: |  |  |  |  |  |  |  |  |
| Depth | SP |  | SN | LN |  | Depth(m) |  | Gamma |

Table 17 Casing arrangement

| Well depth interval from the surface |  | Casing material (steel, PVC) | Diameter (OD), inch | Wall thickness, mm | Connection of casings* | Casing Length(m) |  | Screen opening length, m | Screen opening width, m | % of screen opening | Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| From | To |  |  |  |  | Blind | Screen |  |  |  |  |
| ____''Blind Length, m |  |  |  |  |  |  |  |  |  |  |  |
| ____''screen Length, m |  |  |  |  |  |  |  |  |  |  |  |
| ___''Blind Length,m |  |  |  |  |  |  |  |  |  |  |  |
| ____''Screen Length, m |  |  |  |  |  |  |  |  |  |  |  |
| Total Length, m |  |  |  |  |  |  |  |  |  |  |  |

Table 18 Sieve analysis result by layers

| sieve size (mm) | weight retained (gm) | % retained | % passing |
| --- | --- | --- | --- |
| Total |  |  |  |

Table 19 Preliminary pumping test data

Pump Type: ___________H =____________m

Q = ______l/s

Pump position: __ m Method of Measurement: ____ __If V-notch, Type _____and

Static water level (SWL): __ m. If Artesian Piezometeric head above the surface of the earth: _m

| Date | Time | Water level from the surface, m | Draw down, m | Electrical conductivity (EC), mS/cm | Temp, deg. C | Pumping rate, l/s | v-notch measurement, mm | Turbidity, mg/l | Recovery, wl, m |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Table 20  Step drawdown pumping test

Pump type:  _____	Step test duration:                             hrs

Method of measurement:       (V-notch, volumetric) , Pump position: _____ m Static water level (SWL):  ___ m

| Date Time | Time(min) Since pumping Started | Step 1 |  | Step 2 |  | Step 3 |  | Step 4 |  | Recovery Observation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1= 6.8 l/s |  | Q2= 13.2 l /s |  | Q3= 20.1 l /s |  |  |  |  |
|  |  | WL, m | DD, m | WL, m | DD, m | WL, m | DD, m | WL, m | DD,m | WL, m |

Table 21 Summary of step drawdown test

| Steps | Q | S (Drawdown, m) | Duration (minute) |
| --- | --- | --- | --- |
| Step 1 |  |  |  |
| Step 2 |  |  |  |
| Step 3 |  |  |  |
| Step 4 |  |  |  |

Table 22 Constant rate test data

Constant Test Start Date:                (d/m/y) Constant Test End Date:                                      Constant Test Duration:            hours	  Pump type:  ________	      SWL: _____m

Pump position: _____m   Q:  ___ l/s. If Artesian, Piezometric head above the surface of the earth:

| Date | Time since pumping started, min | Water Level(m) | Draw Down(m) | Discharge Measurement |  | EC, µS/cm | Temp OC |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | V-notch(mm)* | Q(l/s) |  |  |

Table 23 Recovery pumping test data

Recovery Start Date:               (d/m/y) Recovery End Date:                                          Constant Test Duration:     hours	Pump type: _________

SWL:        m	      Pump position:           m 	              Q:            l/s

| Date | Time since Recovery started, min | Water Level(m) | Residual Draw Down(m) | Comment |
| --- | --- | --- | --- | --- |

Table 24 Chemical analysis result of monitoring wells

| Source of sample | Well | Well | Well | WHO max-min (mg/l) |
| --- | --- | --- | --- | --- |
| Location |  |  |  |  |
| Date of collection |  |  |  |  |
| Date received |  |  |  |  |
| Clients ID. NO. |  |  |  |  |
| Lab.ID No. |  |  |  |  |
| Color (app) |  |  |  |  |
| Turbidity(NTU) |  |  |  |  |
| Total Solids 1050c(mg/l) |  |  |  |  |
| T. Dissolved Solid 1050c |  |  |  |  |
| Electrical Conductivity(mS/cm) |  |  |  |  |
| pH |  |  |  |  |
| Ammonia(mg/l NH3) |  |  |  |  |
| Sodium(mg/l Na) |  |  |  |  |
| Potassium(mg/l k) |  |  |  |  |
| Total Hardness(mg/l CaCo3) |  |  |  |  |
| Calcium(mg/l Ca) |  |  |  |  |
| Magnesium(mg/l Mg) |  |  |  |  |
| Total Iron(mg/l Fe) |  |  |  |  |
| Manganese(mg/l Mn) |  |  |  |  |
| Flouride(mg/l F) |  |  |  |  |
| Chloride(mg/l Cl) |  |  |  |  |
| Nitrite(mg/l No2) |  |  |  |  |
| Nitrate(mg/l No3) |  |  |  |  |
| Alkalinity(mg/l CaCo3) |  |  |  |  |
| Carbonate(mg/l CO3) |  |  |  |  |
| Bicarbonate(mg/l HCO3) |  |  |  |  |
| Sulphate(mg/l SO4) |  |  |  |  |
| Phosphate(mg/l PO4) |  |  |  |  |
| Total Coliform Per 100ml |  |  |  |  |
| Fecal Coliform per 100 ml and etc |  |  |  |  |